Appendix C

Sample Implementation Summaries

KliMalasakit Operational Data Unified System (KODUS)

Good Practice Documentation Appendix Package

DSWD Field Office Caraga

Prepared for Knowledge Management documentation review

[MANUAL INPUT REQUIRED: Insert official document date, version, reviewer, and approving official]

# Table of Contents

# Appendix C - Sample Implementation Summaries

This appendix forms part of the KODUS Good Practice Documentation package. It is prepared in formal DSWD Knowledge Management style to provide organized evidence, process notes, and documentary references for review, replication, and institutional learning.

Scope: Synthetic implementation summaries for demonstrating how KODUS supports management review of Project LAWA and BINHI targets, activities, and accomplishments.

Confidentiality notice: All examples in this appendix use sanitized, aggregate, or synthetic data. Screenshots pending owner validation are marked with manual insertion notices. Passwords, tokens, OAuth secrets, beneficiary data, contact details, private host identifiers, and other sensitive values are excluded.

## C.1 Summary Preparation Note

The sample summaries below are illustrative only. They are designed to show the documentary form and review fields expected in the GPD package without disclosing actual beneficiary-level or personally identifiable records.

Table C-. Sample provincial implementation summary

| Province | Municipalities covered | Approved target PBs | Imported/validated PBs | Validation status | Management note |
| --- | --- | --- | --- | --- | --- |
| Agusan del Norte | 3 | 120 | 118 | Partial | Two pending entries subject to source workbook reconciliation. |
| Agusan del Sur | 4 | 180 | 180 | Validated | Counts aligned with approved target records. |
| Surigao del Norte | 2 | 90 | 94 | Over Target | Four excess entries under validation review. |
| Surigao del Sur | 3 | 150 | 150 | Validated | Ready for consolidated reporting. |
| Dinagat Islands | 1 | 45 | 42 | Partial | Three pending entries awaiting field confirmation. |

Table C-. Sample activity accomplishment summary

| Activity area | Synthetic reporting period | Planned activities | Completed activities | Variance | Action point |
| --- | --- | --- | --- | --- | --- |
| Climate-resilient livelihood support | Q1 2026 | 12 | 11 | -1 | Confirm rescheduled activity date. |
| Cash-for-training/work implementation | Q1 2026 | 18 | 18 | 0 | Maintain routine monitoring. |
| MEB validation and reporting | Q1 2026 | 5 | 4 | -1 | Complete pending workbook validation. |
| Monitoring and technical assistance | Q1 2026 | 8 | 8 | 0 | Attach approved monitoring evidence. |

## C.2 Sample Narrative Summary

For the synthetic reporting period, KODUS supported consolidation of target and accomplishment references across covered localities. The dashboard and validation modules enabled management to identify locations with complete validation, partial completion, or records requiring further reconciliation. The generated summaries are intended to support operational decision-making, management review, and preparation of formal reports using controlled and validated source data.

## C.3 Recommended Summary Attachments

The final owner-validated package may attach approved aggregate exports, sanitized screenshots, and signed review sheets. Raw operational workbooks, unmasked beneficiary records, and source files containing personal data shall not be included in the public or KM-facing appendix package.

## C. Owner Validation Checklist

Table C-. Owner validation checklist

| Validation item | Required action | Status |
| --- | --- | --- |
| Sanitization | Confirm no beneficiary-level personal information, account secret, token, or password is visible. | [MANUAL INPUT REQUIRED] |
| Currency | Confirm screenshots, tables, and process notes reflect the approved KODUS build. | [MANUAL INPUT REQUIRED] |
| Sign-off | Record reviewer, date reviewed, and approving official in the title page. | [MANUAL INPUT REQUIRED] |
| Retention | File the validated appendix with the controlled GPD/KM documentation set. | [MANUAL INPUT REQUIRED] |